## 25March
Task | Assigned to | Estimated Effort (hours) | Due Date | Percent Complete | Completion Date | Actual Effort (hours)
Familiarize self with GitHub | Ben | 8 | 2018-03-30
Business Function Model | Eugene | 1 | 2018-03-27
Functional Requirements | Brandon | 1 | 2018-03-27
Review Business Function Model & Functional Requirements | Ben | 1 | 2018-03-27
Turn in Business Function Model & Functional Requirements | Eugene | 0.15 | 2018-03-28
Make (minor) changes to Rules and resubmit to Blackboard | Eugene | 0.5 | 2018-03-30
After group review and approval, turn in Project Plan to Blackboard (weekly) | Eugene | 0.15 | 2018-03-30

## 1April
Task | Assigned to | Estimated Effort (hours) | Due Date | Percent Complete | Completion Date | Actual Effort (hours)
Preliminary Class Design | Ben | 2 | 2018-04-06
After group review and approval, turn in Preliminary Class Design | Ben | 0.15 | 2018-04-06
User Experience Mockup | Brandon & Eugene | 4 | 2018-04-06
After group review and approval, turn in User Experience Mockup | Eugene | 0.15 | 2018-04-06
After group review and approval, turn in Project Plan (weekly) | Eugene | 0.15 | 2018-04-06