## 25 March 2018
Task | Assigned to | Estimated Effort (hours) | Due Date | Percent Complete | Completion Date | Actual Effort (hours)
Familiarize self with GitHub | Ben | 0.5 | 2018-03-30 | 0%
Business Function Model | Eugene | 1 | 2018-03-27 | 100% | 2018-03-25 | 1
Functional Requirements | Brandon | 1 | 2018-03-27 | 100% | 2018-03-25 | 1
Review Business Function Model & Functional Requirements | Ben | 1 | 2018-03-27 | 100% | 2018-03-27 | 1
Turn in Business Function Model & Functional Requirements | Eugene | 0.25 | 2018-03-28 | 100% | 2018-03-27 | 0.25
Make (minor) changes to Rules and resubmit to Blackboard | Eugene | 0.5 | 2018-03-30 | 100% | 2018-03-30 | 0.5
After group review and approval, turn in Project Plan to Blackboard (weekly) | Eugene | 0.25 | 2018-03-30 | 100% | 2018-03-30 | 0.25

## 1 April 2018
Task | Assigned to | Estimated Effort (hours) | Due Date | Percent Complete | Completion Date | Actual Effort (hours)
Familiarize self with GitHub | Ben | 0.5 | ASAP | 100% | 2018-04-04 | 0.5
Preliminary Class Design | Ben | 2 | 2018-04-06 | 100% | 2018-04-06 | 2
After group review and approval, turn in Preliminary Class Design | Ben | 0.25 | 2018-04-06 | 100% | 2018-04-06 | 0.25
User Experience Mockup | Brandon & Eugene | 4 | 2018-04-06 | 100% | 2018-04-05 | 6
After group review and approval, turn in User Experience Mockup | Eugene | 0.25 | 2018-04-06 | 100% | 2018-04-05 | 0.25
Get ahead on next week's assignments | Brandon & Eugene | 2 | N/A | 100% | 2018-04-05 | 3
After group review and approval, turn in Project Plan (weekly) | Eugene | 0.25 | 2018-04-06 | 100% | 2018-04-06 | 0.25

## 8 April 2018
Task | Assigned to | Estimated Effort (hours) | Due Date | Percent Complete | Completion Date | Actual Effort (hours)
Fill out Peer Evaluation Survey I for Brandon & Ben | Eugene | 0.5 | 4/10/18 (start of class) | 100% | 2018-04-06 | 0.5
Fill out Peer Evaluation Survey I for Eugene & Ben | Brandon | 0.5 | 4/10/18 (start of class) | 100% | 2018-04-10 | 0.5
Fill out Peer Evaluation Survey I for Brandon & Eugene | Ben | 0.5 | 4/10/18 (start of class) | 100% | 2018-04-07 | 0.5
Design Alternative Analysis | Eugene | 1.5 | 2018-04-13 | 100% | 2018-04-09 | 2.5
Design Alternative Analysis | Brandon | 2.5 | 2018-04-13 | 100% | 2018-04-09 | 2
After group review and approval, turn in Design Alternative Analysis | Eugene | 0.25 | 2018-04-13 | 100% | 2018-04-12 | 0.25
Test Plan | Eugene | 2 | 2018-04-13 | 100% | 2018-04-09 | 2
Test Plan | Brandon | 1 | 2018-04-13 | 100% | 2018-04-09 | 1.5
After group review and approval, turn in Test Plan | Eugene | 0.25 | 2018-04-13 | 100% | 2018-04-12 | 1.5
Convert all existing code to meet specifications for project | Ben | 4 | 2018-04-13 | 100% | 2018-04-10 | 6
Support Ben on coding | Brandon | 1.5 | 2018-04-13 | 100% | 2018-04-10 | 3
Test code in non-GUI environment | Ben | 0.5 | 2018-04-12 | 100% | 2018-04-10 | 1
Familiarize self with JSwing and implement two GUI panels | Eugene | 2 | 2018-04-12 | 100% | 2018-04-12 | 5
Familiarize self with JSwing and implement two GUI panels | Brandon | 2 | 2018-04-12 | 100% | 2018-04-12 | 3
After group review and approval, turn in Project Plan (weekly) | Eugene | 0.25 | 2018-04-13 | 100% | 2018-04-13 | 0.25

## 15 April 2018
Task | Assigned to | Estimated Effort (hours) | Due Date | Percent Complete | Completion Date | Actual Effort (hours)
GUI: Main Menu, Leaderboard, Instructions, Beginning Game | Ben | 4 | 2018-04-19 | 100% | 2018-04-19 | 3
GUI: Main Menu, Leaderboard, Instructions, Beginning Game | Brandon | 4 | 2018-04-19 | 100% | 2018-04-19 | 9
GUI: Main Menu, Leaderboard, Instructions, Beginning Game | Eugene | 4 | 2018-04-19 | 100% | 2018-04-19 | 9
Begin testing with Junit | Ben | 1 | 2018-04-19 | 100% | 2018-04-19 | 1.5
After group review and approval, turn in Project Plan (weekly) | Eugene | 0.25 | 2018-04-20 | 100% | 2018-04-20 | 0.25

## 22 April 2018
Task | Assigned to | Estimated Effort (hours) | Due Date | Percent Complete | Completion Date | Actual Effort (hours)
Finish GUI Implementation | Ben | 4 | 2018-04-26
Finish GUI Implementation | Eugene | 4 | 2018-04-26
Finish GUI Implementation | Brandon | 4 | 2018-04-26
Final Game Testing | Ben | 4 | 2018-04-26
Begin presentation | Brandon | 2 | 2018-04-26
Begin final report | Eugene | 2 | 2018-04-26
After group review and approval, turn in Project Plan (weekly) | Eugene | 0.25 | 2018-04-27