## 25 March 2018
Task | Assigned to | Estimated Effort (hours) | Due Date | Percent Complete | Completion Date | Actual Effort (hours)
Familiarize self with GitHub | Ben | 0.5 | 2018-03-30 | 0%
Business Function Model | Eugene | 1 | 2018-03-27 | 100% | 2018-03-25 | 1
Functional Requirements | Brandon | 1 | 2018-03-27 | 100% | 2018-03-25 | 1
Review Business Function Model & Functional Requirements | Ben | 1 | 2018-03-27 | 100% | 2018-03-27 | 1
Turn in Business Function Model & Functional Requirements | Eugene | 0.25 | 2018-03-28 | 100% | 2018-03-27 | 0.25
Make (minor) changes to Rules and resubmit to Blackboard | Eugene | 0.5 | 2018-03-30 | 100% | 2018-03-30 | 0.5
After group review and approval, turn in Project Plan to Blackboard (weekly) | Eugene | 0.25 | 2018-03-30 | 100% | 2018-03-30 | 0.25

## 1 April 2018
Task | Assigned to | Estimated Effort (hours) | Due Date | Percent Complete | Completion Date | Actual Effort (hours)
Familiarize self with GitHub | Ben | 0.5 | ASAP | 100% | 2018-04-04 | 0.5
Preliminary Class Design | Ben | 2 | 2018-04-06
After group review and approval, turn in Preliminary Class Design | Ben | 0.25 | 2018-04-06
User Experience Mockup | Brandon & Eugene | 4 | 2018-04-06 | 100% | 2018-04-05 | 6
After group review and approval, turn in User Experience Mockup | Eugene | 0.25 | 2018-04-06 | 100% | 2018-04-05 | 0.25
Get ahead on next week's assignments | Brandon & Eugene | 2 | N/A | 100% | 2018-04-05 | 2
After group review and approval, turn in Project Plan (weekly) | Eugene | 0.25 | 2018-04-06

## 8 April 2018
Task | Assigned to | Estimated Effort (hours) | Due Date | Percent Complete | Completion Date | Actual Effort (hours)
Fill out Peer Evaluation Survey I for Brandon & Ben | Eugene | 0.5 | 4/10/18 (start of class)
Fill out Peer Evaluation Survey I for Eugene & Ben | Brandon | 0.5 | 4/10/18 (start of class)
Fill out Peer Evaluation Survey I for Brandon & Eugene | Ben | 0.5 | 4/10/18 (start of class)
Design Alternative Analysis | Eugene | 1.5 | 2018-04-13
Design Alternative Analysis | Brandon | 2.5 | 2018-04-13
After group review and approval, turn in Design Alternative Analysis | Eugene | 0.25 | 2018-04-13
Test Plan | Eugene | 2 | 2018-04-13
Test Plan | Brandon | 1 | 2018-04-13
After group review and approval, turn in Test Plan | Eugene | 0.25 | 2018-04-13
Begin coding (start by creating structure) | Ben | 4 | 2018-04-13
Support Ben on coding | Brandon | 1.5 | 2018-04-13
After group review and approval, turn in Project Plan (weekly) | Eugene | 0.25 | 2018-04-13